## Fee Breakdown
		Approach (A)		Approach (B)		Approach (C)
%	Phase	% Const. Costs	Not-To-Exceed	% Const. Costs	Not-To-Exceed	% Const. Costs	Not-To-Exceed

5.0%	Phase 1: / Programming	0.4%	$128	0.5%	$143	0.5%	$158
15.0%	Phase 2: / Schematic Design	1.3%	$383	1.4%	$428	1.6%	$473
20.0%	Phase 3: / Design Development	1.7%	$510	1.9%	$570	2.1%	$630
35.0%	Phase 4: / Construction Documents	3.0%	$893	3.3%	$998	3.7%	$1,103
5.0%	Phase 5: / Bidding & Contract Negotiation	0.4%	$128	0.5%	$143	0.5%	$158
20.0%	Phase 6: / Construction Administration	1.7%	$510	1.9%	$570	2.1%	$630

100.0%	All Phases	8.5%	$2,550	9.5%	$2,850	10.5%	$3,150
Assuming a Construction Cost =							$30,000

## Hour Breakdown
Square Footage - Existing	7,000 SF
Dollar per Square Footage	115 $/SF
Total Estimated Construction Costs	$75,000.00
Architecture Fees - Percentage of Construction	8.5%
Architecture/Engineering Fees	$6,375.00

Average ($/Hr) Billing Rate	$55.00
		Each Phase	Cumulative	Hours dedicated to each phase	weeks - 1/2 person	weeks - 3/4 person	weeks - 1 person	weeks - 1.5 person	weeks - 2 people
Phase 1 - Programming	5.00%	$127.50	$127.50	2 hrs	0.1 wks	0.1 wks	0.1 wks	0.0 wks	0.0 wks
Phase 2 - Schematic	15.00%	$382.50	$510.00	7 hrs	0.3 wks	0.2 wks	0.2 wks	0.1 wks	0.1 wks
Phase 3 - Design Development	20.00%	$510.00	$1,020.00	9 hrs	0.5 wks	0.3 wks	0.2 wks	0.2 wks	0.1 wks
Phase 4 - Construction Documents	35.00%	$892.50	$1,912.50	16 hrs	0.8 wks	0.5 wks	0.4 wks	0.3 wks	0.2 wks
Phase 5 - Bidding and Construction Contract Negotiation	5.00%	$127.50	$2,040.00	2 hrs	0.1 wks	0.1 wks	0.1 wks	0.0 wks	0.0 wks
Phase 6 - Construction Administration	20.00%	$510.00	$2,550.00	9 hrs	0.5 wks	0.3 wks	0.2 wks	0.2 wks	0.1 wks
	100.00%	$2,550.00	$2,550.00	46 hrs	2.3 wks	1.5 wks	1.2 wks	0.8 wks	0.6 wks

Architecture	8.5%	100%	$2,550.00